## Risk Log
Risk ID | Category | Description | Severity | Likelihood | Observed vs Expected | Potential Root Cause | Undocumented Knowledge Dependency
1 | Revenue | Churn spike in Q2 | High | Medium | 12% vs 5% | Customer onboarding friction or product reliability issue | Only known by customer success leads
2 | Finance | Manual revenue reconciliation required monthly | High | High | Multiple adjustments per close | Legacy billing system limitations | Finance senior analyst maintains manual process
3 | Operations | Delayed onboarding timelines | High | Medium | 2 week delay average | Manual data migration and QA processes | Ops team undocumented scripts
4 | Customer Contracts | Enterprise contract exceptions not tracked centrally | Medium | High | ~15% enterprise clients | Custom negotiated SLAs | Customer success personal tracking spreadsheets
5 | Systems | ERP migration incomplete | High | Medium | Delayed 2 quarters | Data mapping issues across product modules | ERP migration logic known by small engineering group
6 | Support | Ticket backlog growth in enterprise tier | Medium | Medium | Backlog doubled in 6 months | New product instability or onboarding gaps | Support escalation workflows undocumented